## Sheet1
Name (Green=completed, yellow=in progress) | Description | Point Value | Status
Production Launch | Launch to server | 8 | Completed
Manual Data Upload | Add the ability, that Dennis requested, to manually enter in new matched data (that you could confirm through your own research). | 8 | Completed
Waiting and Loading Functionality | Add waiting and loading functionality to the data upload and dump restore screens, so that the user cannot interact with the site until it is complete. This will be indicated by a pop up message. | 5 | Completed
Documentation and Comments | Make documentation and comment our code more | 5 | Completed
More robust data matching process | Come up with a way to get more matches uses methods such as levenshtein distance and looking at boarding schools | 5 | Completed
Database Version Control | Implement a version control system for our back-end database | 8 | Completed
CSS Refinements | make the site beautiful | 3 | Completed
UI Enhancements | Display the data in a better way with the table. When a user zooms in on the map of an area, the tables should update accordingly. Add in appropriate filters that the customer wants. Clean up the drop pins so there is only one drop pin per high school, and display the player information more coherently and in an organized way. Display a clickable bio links of players. UI necessities: Figure out how to post data with ajax so page doesn't refresh. If a league is selected, all colleges in that league should be preselected on the UI. When an ajax call is made, a loading bar with soccer balls should be visible | 5 | Completed
Django & Database Integration | Review Django framework that the team last semester used. Make the necessary modifications to fit with out new database. | 2 | Completed
Matching High School Names across tables | Figure out a robust, accurate, and persistent way to match the high school names in the public database to our tables so we know locations of the schools. | 8 | Completed
Building a Database | We need to rebuild the current database and make schema to incorporate cleaner tables for our project. We also need to find a way to consolidate the players in our roster table so there are no duplicate players across roster years. At the same time, we need to makes sure all data persists after grouping. | 5 | Completed
GPS Coordinates for Foreign High Schools | Geocode the foreign high schools csv data | 3 | Completed